## Sheet1
Task Name | Start | End | Duration (days)
Group Introduction and exchanging contacts and info | 2017-01-24 | 2017-02-02 | 9
Project idea and ways of implementation | 2017-02-02 | 2017-02-11 | 9
Design a project plan with milestones and deliverables | 2017-02-14 | 2017-02-25 | 11
Design of UML graphs and System Design | 2017-02-22 | 2017-03-05 | 11
System Development with Python (Tkinter and SQLite) | 2017-02-28 | 2017-03-20 | 20
Solution evaluation and Improvements | 2017-03-18 | 2017-03-24 | 6
Individual Reports and Finalizing project | 2017-03-25 | 2017-04-03 | 9